| ACP Testing Workgroup Meeting |  |  |  |  | Agenda: | X | Minutes: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Facilitator: | Healtheway |  | Date: | 1/23/2015 |  |  |  |  |
| Note taker: | Juan C. Fourquet |  | Time: | 12-1:00PM (EST) |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |
| Ahmed; , Shuvo. |  | Hill; , David. |  |
| Bartlett; , Janis. |  | Kim, Seonho |  |  |  |  |  |
| Borden; , David. |  | Lamy; , Joe. |  |
| Corsi, Kyle |  |  | Lomangino; , Mike. |  |
| Davis; , Didi. |  | Moehrke; , John. |  |
| Donnelly; , John. |  | Murray, Anthony |  |  |  |  |  |
| Fourquet; , Carlos. |  | Pack; , Henry. |  |
| Harrell, Nan |  |  | Prahl, Martin |  |  |  |  |  |
| Heflin; , Eric.. |  | Rosas, Jennifer |  |  |  |  |  |
| Hernando; , Gonzalo. |  | Ruf,; Lee-Ann. |  |
| Hudson, Gretchen |  |  | Schramm; , David. |  |
| Helman, Jeff |  |  | Tyburski. Michael |  |  |  |  |  |
| Lanigan-Jones, Princess |  |  | Whitecar, Michelle |  |  |  |  |  |

Agenda

- Overall Pilot update and next steps

- Update on the Pilot Testing with SSA Status

  - IOD

  - Mirth

  - MRO

- CC Meeting update (Meeting changed to 2/20/2015)

- General Q&A from Group

Documents:

- 2014_12_19_ACP_SSA_Profile_Test_Cases_withComments.docx

- 2014-12-19_CL_Access_Consent_Policy_ACP.xlsx

Action Items:

| ID | Description | Owner | Date Opened | Date Due | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Review Artifacts Distributed 7/18/2014 with comments by participants | ACP Workgroup Members | 7/18/2014 | 7/25/2014 | Completed |
| 2 | Posting of Comment Forms and Resolutions | ACP Chairs and Healtheway Staff | 7/18/2014 | 08/11/2014 | Completed |
| 3 | Incorporate edits to Artifacts | ACP Chairs and Healtheway Staff | 7/18/2014 | 08/04/2014 | Completed |
| 4 | Review Final Draft of Artifacts | ACP Workgroup Members | 7/11/2014 | 8/08/2014 | Completed |
| 5 | Approval of SSA Phase One Testing Artifact | ACP Workgroup Members | 7/18/2014 | 8/11/2014 | Completed |
| 6 | Test Tool Development | Healtheway/Aegis | 8/2014 | 9/30/2014 | Completed |
| 7 | SOW Executed with Aegis | Aegis/Healtheway Staff | 8/21/2014 | 9/15/2014 | Completed |
| 8 | Communication of Target Date for Pilot to Begin | Healtheway Staff | 8/22/2014 | 9/15/2014 | Completed |
| 9 | Phase 1 – Peer to Peer testing – Test tool development | Pilot Participants/ Hew Staff | 9/15/2014 | 10/31/2014 | Completed |
| 10 | Phase 2 – Automated Testing with DIL | Pilot Participants/ HeW Staff | 9/30/2014 | 12/2014 | Completed |
| 11 | Phase 3 – Participant Testing with SSA Megahit Testing Environment | Pilot Participants/ SSA Staff | 11/2014 | 02/2015 | IOD – Done Mirth – In process MRO – In process |
| 12 | Presentation to Specification Factory for Approval | Healtheway Staff | 8/2014 | 10/09/2014 | Completed |
| 13 | Update Testing Documents with lessons learned from Testing Pilot | Healtheway Staff | 11/2014 | 02/2015 | Last updated documents were distributed 12/19/2014. |
| 14 | Presentation to the Coordinating Committee for Discussion and Approval | Healtheway Staff | 10/2014 | 01/2015 | Information update to CC on 1/20/2015. Production date TBD |